## Intro
4th Year Software Test Plan
Project Name | Login Console
Project Manager | Naomi Hurley
Prepared by | Naomi Hurley and the 4th year Computing students
Tech Lead | To be confirmed
Date
Revision History
Revision | Author | Comment
1 | Naomi Hurley | Initial Draft

## Product No 1 or Sprint No 1
|  | Purpose: | This set of tests is intended to check main functionality developed
RNGFighter |  |  |  | Visual Studio 17 Android Emulator Xamarin UWP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Expected Result | Actual Result | Results Pass/Fail | Bug # | Comments
1 | 1 | TC.001 | Main Menu display | GUI | 1. Launch Application | Compile. | Main Menu page is presented | Main Menu page is presented | Pass
2 | 1 | TC.002 | Display MainMenu | GUI | 1. Launch Application 2. Navigate to Main Menu Page | Compile. | All buttons and images are present with correct design. | Main Menu Grid is presented | Pass
3 | 1 | TC.003 | Music | Functionality | 1. Launch Application 2. Navigate to Main Menu 3. Listen for background music. | Music. | A non-copyrighted song should be beginning to play once the application is launched. | Background music is present. | Pass
3.1 | 1 | TC.003.1 | Music | Functionality | 1. Launch Application 2. Navigate to Main Menu 3. Listen for background music. 4. Click Mute button. | Music. | The background music should be muted, if pressed again should be played. | Mute/Unmute works. | Pass
4 | 1 | TC.004 | Exit | Functionality | 1. Launch Application 2. Navigate to Main Menu 3. Click Quit button to exit the application. | Exit. | The application is closed down without error. | No function. | Fail | Defect No 12346 Priority-1 Severity-Minor | To be assigned
5 | 1 | TC.005 | Navigation | Functionality | 1. Launch Application 2. Navigate to Main Menu. 3. Click New Game button. | Navigation. | Successful navigation. | Succesful navigation from Main Menu to Main Page. | Pass
6 | 1 | TC.006 | Navigation | Functionality | 1. Launch Application 2. Navigate to Main Menu. 3. Click Load Game button. | Navigation. | Successful navigation. | Successful navigation from Main Menu to Saves page. | Pass
7 | 1 | TC.007 | Navigation | Functionality | 1. Click Load Game button. 2. Click Return button. | Navigation. | Navigated back to Main Menu page. | Navigated back to Main Menu page. | Pass
7.1 | 1 | TC.007.1 | JSON | Functionality | 1. Launch Application. 2. Click Load Game button. 3. Click any of the Save buttons. | JSON storage. | Successfully deserializes the json file to retrieve information and continue the game. | JSON code present, not functioning properly/at all. | Fail | Defect No 12347 Priority-1 Severity-Severe | To be assigned
8 | 1 | TC.008 | Main Page display | GUI | 1. Launch Application. 2. Click New Game button. | Correct user interface. | All images and other functions are present. | Everything is present. | Pass
9 | 1 | TC.009 | Buttons MainPage | Functionality | 1. Launch Application. 2. Click New Game button. 3. Click any of buttons labelled 1,2 or 3 to retrieve an alert. | Random Generation | Eventually an alert is trigerred by the user which adds a score point. | An alert pops up and adds +1 to the score. | Pass
10 | 1 | TC.010 | Buttons MainPage | Functionality | 1. Launch Application. 2. Click New Game button. 3. Click one of the buttons labelled 1,2 or 3 repeatedly. | Random Generation | Eventually an alert is trigerred by the user which adds a score point. | No alert, no score. | Fail | Defect No 12348 Priority-1 Severity-Severe | To be assigned
11 | 1 | TC.011 | Stopwatch | Functionality | 1. Launch Application. 2. Click New Game button. 3. Click Start button. | Stopwatch. | The timer should start counting up. | Stopwatch begins. | Pass
12 | 1 | TC.012 | Music | Functionality | 1. Launch Application 2. Navigate to MainPage. 3. Listen for background music. 4. Click Mute button. | Music. | The background music should be muted, if pressed again should be played. | Mute/unmute in mainpage works. | Pass
13 | 1 | TC.013 | Navigation | Functionality | 1. Launch Application 2. Navigate to MainPage. 3. Click Arrow key top left. | Navigation. | Successfuly navigates back to main menu. | Successfuly navigates back to main menu. | Pass

## Product No 2 or Sprint No 2
|  | Purpose: | This set of tests is intended to check main functionality developed
Test Run Title e.g. Login validation |  |  |  | Microsoft Internet Explorer 9 Windows 7 Microsoft Internet Explorer 10 Windows 7 Micresoft Internet Explorer 11 Windows 7 Microsoft Internet Explorer 8 Windows XP Microsoft Internet Explorer 7 Windows XP Firefox latest version Apple Safari Windows XP Apple Safari Google Chrome Windows XP Opera Windows XP
Requirement ID | Sprint | Test Case Ref | Test Case Name | Descriptions | Search Parameters / Instructions | Checks | Results Pass/Fail | Bug # | Comments

## Test Progress
Tabs | Developped by | No of test cases | Tester | No of days | Browsers | Test cases passed | Test cases failed | To be done | Percentage done
Sprint No
Test Run description | Team A | 18 |  |  | All | 0 | 0 | 18 | 0%
Test Run description | Team B | 8 |  |  | N/A | 0 | 0 | 8 | 0%
Test Run description | Team C | 19 |  |  | All | 0 | 0 | 19 | 0%
Test Run description | Team D | 20 |  |  | All | 0 | 0 | 20 | 0%
Test Run description | Team C | 42 |  |  | All | 0 | 0 | 42 | 0%
Total |  | 107 |  |  |  |  | 0 | 0 | 0%